## Weekly
Steps | Already done | Week of 16/11/15 | Week of 23 and 24 | Week of 30/11/15 | Week of 07/12/15
Interaction with locals | ✔
Observed basic dynamics of the lot | ✔ |  |  |  |  | Done
Permission to use F&V wall | ✔ |  |  |  |  | In progress
Memorial design | ✔ |  |  |  |  | Late
Mural designer | ✔ |  |  |  |  | Mural
Mural idea | ✔ |  |  |  |  | Memorial
Current lot dynamics defined |  | ✔ |  |  |  | Proposal
Final colored mural design (Lenny) |  | ✔
Find out how and by when wall can be prepped |  | ✔
Find out prices and places to buy paint |  | ✔ | ✔
Finalize Memorial Design (Benches included) |  | ✔ | ✔

## Mural
Steps | Week of 16/11/15 | Week of 23 and 24 | Week of 30/11/15 | Week of 07/12/15
B&W paper drawing | Sunday
Coloring B&W paper | Monday |  |  |  | Done
Final mural design with colors | Tuesday |  |  |  | In progress
Talk to Chop Chop guy | Monday/Tuesday |  |  |  | Late
Paint type | Wednesday
Wall prep - methods | Wednesday
Have flyer design ready | Wednesday
Paint prices and prospective vendors | Thursday
Have flyer on the door | Thursday
Wall prepped |  | Wednesday
Have paint |  | Wednesday
Check on wall progress |  |  | Thursday

## Memorial
Steps | Week of 16/11/15 | Week of 23 and 24 | Week of 30/11/15 | Week of 07/12/15
Visit stores and price brick and paint | ✔
Ask Ricky/Jesse about labor | ✔ |  |  |  | Done
Visit CTP/Greenpop | ✔ | ✔ |  |  | In progress
Ask F&V manager about trees | Tuesday |  |  |  | Late
Find out memorial prep | ✔ | ✔ |  |  | Not doing
Find out prices and places to buy bricks, paint and plaques | ✔ | ✔
Buy Bricks and try them out |  | ✔

## Budget
Project Budget (R)
Total:
| Item | Price | Paid? (Y/N) | Payment Deadline | Reimbursed? (Y/N) | Who Paid? | Needs to be Reimbursed Next | 0
Memorial | Gabion Baskets |  | Yes |  | Yes
Mural | Materials (paint, paintbrushes, chalk, masking tape, roller, chalk line) |  | Yes |  | Yes |  | Received | Date | Leftover | Notes
| Materials |  | Yes |  | Yes
| Stencils printing |  | Yes | Monday 12/07 | Yes
| Flowers |  | Yes | Monday 12/07 | Yes | -
| Plaques |  | Yes | Monday 12/14 | Yes | -
| Concrete |  | Yes | Friday 12/11 | Yes | -
| Spent | 0
| Remaining | 0